## Feature Backlog
User Story ID | As <a type of user> | I want to <perform some task> | so that I can <achieve some goal> | Acceptance Criteria | Notes | Status | Priority | Theme | Story Points | Sprint # |  | Total Story Points | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Contractor | have old cabinets and appliances removed | prepare for the new kitchen |  |  | Complete | H | Demolition | 5 | 1 | Target | 53 | 43 | 33 | 23 | 13 | 3 | 0
3 | Owners | Have a temporary basement kitchen area | continue to feed the family during the construction |  |  | Complete | H | Rough-ins | 3 | 1 | Remaining Story # | 53 | 1: 45; 2: 36
6 | Owner | Have VacuSweep Inlet (floor level central vac inlet) | convice the . kids that sweeping the floor is fun |  | Incomplete in 1st iteration due to problem routing vacume tubes | Complete | L | Rough-ins | 2 | 1
2 | Contractor | remove existing floor tiles and backsplash | prepare for new floor and backsplash |  |  | Complete | H | Demolition | 7 | 2
4 | Dad | have ceiling speakers in the kitchen | listen to classic rock while preparing dinner |  | Incomplete in 2nd iteration | Complete | M | Rough-ins | 1 | 2
7 | Owner | have a small island sink in addition to the main one | preparing fruits and vegetables while my spouce prepares dinner |  |  |  | M | Rough-ins | 2 | 2
14 | Mom | move the diswasher to the other side of the main sink | have more drawer space next to kitchen table |  |  |  | H | Rough-ins | 3 | 3
16 | Mom | have a wood floor | stand for long periods of time while preparing meals without my feet getting tired! |  |  |  | M | Rough-ins | 4 | 3
5 | Owner | Have all new appliances | save money with energy efficient appliances |  |  |  | H | Finishes | 1 | 4
8 | Owners | have a kitchen desk | make dinner while watching the kids do their homework |  |  |  | H | Built-ins | 4 | 4
9 | Dad | have new shelving in pantry | store bulk supplies from Costco |  |  |  | H | Built-ins | 4 | 5 | bar: 7
10 | Mom | have california shutters on windows | control the amount of sun that gets into the room |  |  |  | L | Finishes | 2 | 5
11 | Owners | have a built in microwave | keep the microwave out of reach of the kids |  |  |  | H | Rough-ins | 3 | 3
12 | Owners | have a glass tile backsplash | have a modern looking kitchen |  |  |  | H | Finishes | 4 | 6
13 | Owners | Have all new cabinets with soft close hardware | the kids will no longer be able to slam the doors |  |  |  | H | Built-ins | 5 | 4
15 | Dad | Repaint the walls | hide the thousands of fingerprints |  |  |  | M | Finishes | 3
Total | [8 empty] | 53
This simple Excel template is an example of an Feature Backlog template. The data is simulated and is only meant to serve as an example. Your actual Iteration Backlog may benefit from information columns not included here.
The information in the spreadsheet table can easily be merged onto the MS Word template used to print user stories onto 3 x 3 post-it notes (as was done for the course).
Use the data in the "Look-up list" tab to chagne the information that can appear in the Status, Theme, and other columns where information is restricted.
Use the autofilter capability to quickly sort stories by feature, and filter by priority. This is useful when planning sprints.

## Iteration Backlog
Story # | Backlog Item | Theme | Priority | Story Points | Responsible | Status | Original Estimate (hrs) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
2 | Remove existing floor tiles and backsplash | Demolition | H | 7 |  |  | 53 | 47 | 37 | 18 | 8
| Lift-up existing floor tiles |  |  |  |  | Complete | 21 | 16 | 10 | 6 | 0
| screw down new 1/4in plywood to sub-floor |  |  |  |  | In Progress | 14 | 14 | 14 | 7 | 3
| Remove existing backslash tiles |  |  |  |  | Complete | 6 | 6 | 3 | 0
| Repair damage to drywall |  |  |  |  | To Verify | 4 | 4 | 4 | 0
| Place old tiles in bin for disposal |  |  |  |  | In Progress | 4 | 3 | 2 | 1 | 1
| Take scrap tiles to dump site |  |  |  |  | Not Started | 2 | 2 | 2 | 2 | 2
| Clean area and prepare for new floor |  |  |  |  | Not Started | 2 | 2 | 2 | 2 | 2
6 | Rough-in ducting for VacuSweep | Rough-in | L | 2 |  |  | 5 | 5 | 5 | 5 | 4
| Install vacuum duct around support beam |  |  |  |  | In Progress | 2 | 2 | 2 | 2 | 1
| glue all joints |  |  |  |  | Not Started | 2 | 2 | 2 | 2 | 2
| Test system |  |  |  |  | Not Started | 1 | 1 | 1 | 1 | 1
4 | Rough-in wiring for ceiling speakers | Rough-in | M | 1 |  |  | 3.5 | 3.5 | 3.5 | 3.5 | 7.5
| Cut holes for fishing wiring through walls |  |  |  |  | Complete | 0.5 | 0.5 | 0.5 | 0.5 | 0
| Cut holes in ceiling for speakers |  |  |  |  | Complete | 0.5 | 0.5 | 0.5 | 0.5 | 0
| Rough-in volume contol knob |  |  |  |  | Not Started | 1 | 1 | 1 | 1 | 1
| Fish wires from family room to kitchen ceiling |  |  |  |  | In Progress | 1 | 1 | 1 | 1 | 6
| Test system |  |  |  |  | Not Started | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| Total hours remaining |  |  | 10 |  |  | 61.5 | 55.5 | 45.5 | 26.5 | 19.5
[7 empty] | 61.5 |  |  |  |  | 0
This simple Excel template is an example of an Iteration Backlog template. The data is simulated and is only meant to serve as an example. Your actual Iteration Backlog may benefit from information columns not included here.

## Look-up lists
Priority | Stutus | Theme
H | Not Started | Demolition
M | In Progress | Rough-ins
L | Complete | Built-ins
| Incomplete | Finishes
To Verify